## Master List of Actions
Code Associated with the Co-Developed Action | Public Health Emergency | Health Province, Region, State, etc. | Health District, Region, Zone, Jurisdiction, Division, etc. | Health Precinct, Sector, Territory, Area, Unit, Locale, etc. | Date of Co-Development Session (yyyy-mm-dd) | Year | Quarter | Source Analysis/Link in Drive | Key Risks/ Observations | Contributing Factors | Underlying Causes | Co-Developed Actions | Objective of the Action | Action Category | Population Affected by the Action | How Action(s) will be Verified (i.e., source) | Actor(s)/Partner(s) Responsible for the Action | Contact Person Responsible for the Action | Actor/ Partner Category | Sector [of Partner] Responsible for the Action | Date Action(s) are Implemented (yyyy-mm-dd) | Follow-Up Date (yyyy-mm-dd) | Implementation Status | Reason for Delay or Abandonment of the Action | Link to Verification Source | Indicator(s) Measuring Impact (correlation, not causality) | Effect/Impact of the Implemented Action | Narrative
Create a unique code designed specifically for each co-developed action. Every action should have its own distinct code. For example, an action co-developed during a polio outbreak in 2024 might be assigned a code such as 'Polio24_001'. Ensure that this code corresponds to the code listed in column L on the second tab of this Excel spreadsheet. | List the name of the public health emergency being addressed, along with the specific IOA approach used. This could involve rapid investigations for newly emerging diseases in new locations or high-risk areas, or ongoing investigations for recurrent outbreaks. Example: 'Ongoing Investigation of Polio Recurrence'. | List the geographic administative divison in your country where the public health emergency is occuring. This could be a province, state, region, or similar area. | Provide the specific health district, region, zone, jurisdiction, or division within the geographic administrative division (such as a province, state, or region) previously listed, where the public health emergency is occurring. This should be a more localized area within the broader administrative division you identified. | Specify the precise health precinct, sector, territory, area, unit, or locale within the broader health district, region, zone, jurisdiction, or division you previously identified. This should pinpoint the most localized area where the public health emergency is taking place, nested within the larger geographic administrative division (such as a province, state, or region) you listed earlier. | List the date of the co-development session where the action was formulated and assigned. | List the year in which the co-developed actions were formulated to address the public health emergency. | List the quarter in qhich the co-developed actions were formulated to address the public health emergency. | Each response should include a shared folder containing analyses that detail the observed key risks, contributing factors, and underlying causes. Provide a link to the documents containing the analysis that highlights these observations and informed the co-developed action. Examples include the co-developement session presentations, MONITITOs, etc. | List the key risks and observations linked ot the co-developed aciton. For instance, in the case of a recurring polio outbreak, a noteable risk could be that infants are not receiving vaccinations. | List the contributing factors associated with the co-developed action. For instance, a contributing factor for infants not receiving vaccinations could be the prevalence of at-home deliveries, which often result in reduced access to post-natal care. | List the underlying causes associated with the co-developed action. For example, the high prevalence of at-home deliveries, leading to infants missing post-natal care such as vaccinations, can be attributed to the high cost of helathcare services and insufficient transportation to clinics. | List the co-developed acitons that were formulated specifically to address the identified contributing factors and underlying causes. | Describe the objective of the co-developed action: What is the indented purpose or reason behind the action? What specific issues or challenges does it aim to address? | Choose the action category that the co-developed action falls under. Examples include advocacy for financing, changes to strategies, and new program development and implementation. Collecting this data aids in internal analysis to identify trends in the types of actions being pursued. If a particular type of action predominates, we can investigate the reasons behind this pattern. | Select the population that this co-developed action is designed to impact or affect. Examples include children, women, men, or global (everyone). | Describe the method for verifying the co-developed action. Verification could be domonstrated through various forms of documentation, such as attendance lists, reports, meeting minutes, policy updates, or revised budgets. | List the name of the actor(s)/partner(s) who are responsible for the co-developed action. | Provide the anme and contact information, including email and phone number, of the individual responsible for overseeing the co-developed actions and updating the IOA team. | Select the category that best describes the actor or partner responsible for implementing and overseeing the co-developed action. Examples include UN Agency, National Government, Local Government, NGO, etc. | Select the sector of the partner responsible for implementing the action. Example sectors include Health, Agriculture, WaSH, Risk Communication and Community Engagement, among others. | List the date that the co-developed action is implemented. | Specify the date for the follow-up on the co-developed actions. During this follow-up, the IOA team will engage with the designated contact person responsible for overseeing and reporting on the action. This meeting will provide an opportunity to review progress, discuss implementation details, and learn of any outcomes associated with the action. | Select the implementation status category for the action from the following options: completed, in-progress, delayed/not yet started, or abandoned. | List any resons for the delay or abandonment of the co-developed actions. | Provide links to sources that can confirm the implementation status of the action. Refer to the previously specified verification methods under 'how action(s) will be verified' and attach the corresponding documents. Examples of such documents include attendance lists, reports, meeting minutes, policy updates, and updated budgets. | Specify the indicators that will be used to assess the impact of the action on the contributing factors and underlying causes identified. Detail the metrics that will be tracked to evaluate whether the action has successfully mitigated the contributing factors and addressed the underlying causes related to the observed risk or problem. | List any effects or impacts associated with the implemented co-developed action. If no changes or impacts are observed, specify that as well. | Provide any additional details related to the assessment of the co-developed action, including: Assessor's Information (who conducted the assessment); Evidence/Documentation (link or describe any documents or evidence used to support the assessment findings); and Next Steps (outline the subsequent actions to be taken, especially if no change or improvement was observed. What are the planned measures to address any continuing issues or to build on successes?).
Polio24_001 | Ongoing Investigation of Polio Recurrance | Province: Verdantis | Health Zone: Azure Reach | Health Area: Lumoria | 2024-07-15 | 2024 | Q3 | https://www.LINK TO SHARED FOLDER.org | Poor Sanitation in Lumoria. Poor sanitation is linked to malnutrition, which can compromise the immune system and diminish vaccine effectiveness. This weakened immune response increases vulnerability to diseases such as polio. | Lack of access to clean water | Inadequate infrastructure in Lumoria due to limited funding and/or prioritization of water treatment projects | Increase funding allocations for rural water treatment projects through governmental budgets or international aid. | Secure financial resources to expand and enhance water treatment facilities in rural areas, ensuring sustainable water access. | Advocacy for Financing | Global | Approval documents and funding disbursement reports. | Global Water Initiatives | Sarah Chen, sarah.chen@gwi.org, +123-456-7890 | International Non-Governmental Organization (INGO) | Logistics | 2024-08-15 | 2024-09-15 | In-Progress | N/A | https://www.LINK TO VERIFICATION DOC.org | Amount of funds allocated, number of projects initiated. | Improved access to clean water in rural areas. | Assessor's Information: Sarah Chen, Finance Manager Evidence/Documentation: Funding approval documents and budget reports. Next Steps: Monitor fund utilization and initiate additional funding requests as needed.
Polio24_002 | Ongoing Investigation of Polio Recurrance | Province: Verdantis | Health Zone: Azure Reach | Health Area: Lumoria | 2024-07-17 | 2024 | Q3 | https://www.LINK TO SHARED FOLDER.org |  |  |  | Develop partnerships with local organizations and communities to build and maintain water treatment infrastructure using sustainable, locally sourced materials and techniques. | Collaborate with local stakeholders to build water infrastructure that leverages sustainable practices and local resources, promoting community ownership and long-term viability. | Advocacy for New Strategy Development | Global | Partnership agreements and project initiation reports. | EcoWater Solutions | Jamal Youssef, jamal@ecowatersolutions.com, +987-654-3210 | Civil Society Group | Water, Sanitation, & Hygiene (WASH) | 2024-08-20 | 2024-09-20 | Completed | N/A | https://www.LINK TO VERIFICATION DOC.org | Number of partnerships formed, infrastructure projects started. | Enhanced local capacity for sustainable water management. | Assessor's Information: Lisa Smith, Project Manager Evidence/Documentation: Signed agreements and project reports. Next Steps: Expand partnerships and scale up successful models.
Polio24_003 | Ongoing Investigation of Polio Recurrance | Province: Verdantis | Health Zone: Azure Reach | Health Area: Lumoria | 2024-07-18 | 2024 | Q3 | https://www.LINK TO SHARED FOLDER.org |  |  | Travel to areas with access to clean water is unsafe | Work with local actors to enhance safety measures for routes used to access clean water. | Improve the safety and accessibility of pathways leading to water sources, ensuring that communities can safely access clean water. | Direct Change to Strategy | Women | Safety audit reports and community feedback. | Local Health Authority | Linda Gregor, linda@swpathways.com, +456-789-0123 | Local Health Authorities | Protection including Gender-based Violence (GBV) | 2024-08-25 | 2024-09-25 | Delayed/Not Yet Started | Procurement issues. | https://www.LINK TO VERIFICATION DOC.org | Reduction in safety incidents, community satisfaction. | N/A - action not yet implemented. Anticipating safer access to water resources and improved community well-being. | Assessor's Information: Michael Johnson, Safety Officer Evidence/Documentation: Audit documents and community surveys. Next Steps: Resolve procurement issues and complete safety enhancements
Polio24_004 | Ongoing Investigation of Polio Recurrance | Province: Verdantis | Health Zone: Azure Reach | Health Area: Lumoria | 2024-07-21 | 2024 | Q3 | https://www.LINK TO SHARED FOLDER.org |  |  |  | Establish localized water purification systems (e.g., rainwater harvesting, community wells) within communities to minimize the need for travel to distant water sources. | Reduce dependency on distant water sources by developing localized water purification and collection systems, enhancing water availability and reducing travel burdens. | New Program Development & Implementation | Women | Installation records and water quality tests. | Community Water Hub | Mark DuPont, mark@communitywaterhub.org, +321-654-0987 | Community | Water, Sanitation, & Hygiene (WASH) | 2024-08-30 | 2024-09-30 | In-Progress | N/A | https://www.LINK TO VERIFICATION DOC.org | Number of systems installed, improvement in water quality. | Increased availability of clean water, reduced disease incidence. | Assessor's Information: Angela White, Environmental Engineer Evidence/Documentation: Installation receipts and water quality reports. Next Steps: Complete installations and conduct follow-up water quality assessments.
Polio24_005 | Ongoing Investigation of Polio Recurrance | Province: Verdantis | Health Zone: Azure Reach | Health Area: Lumoria | 2024-07-22 | 2024 | Q3 | https://www.LINK TO SHARED FOLDER.org |  | Poor waste disposal | Inadequate maintenance of sewage systems leads to community concerns about disease risks associated with using communal latrines | Establish a regular maintenance schedule for sewage systems and allocate sufficient funds and personnel to ensure operations are carried out. | Ensure the efficient and continuous operation of sewage systems through regular maintenance and adequate resource allocation. | New Program Development & Implementation | Global | Maintenance logs and inspection reports. | Ministry of Health | Roberto Alvarez, roberto@usd.gov, +213-864-1309 | Ministry of Health | Water, Sanitation, & Hygiene (WASH) | 2024-08-05 | 2024-09-05 | Completed | N/A | https://www.LINK TO VERIFICATION DOC.org | Frequency of maintenance performed, system reliability. | Improved sanitation and reduced environmental contamination. | Assessor's Information: Robert Green, Sanitation Supervisor Evidence/Documentation: Maintenance schedules and logs. Next Steps: Increase maintenance frequency based on system demands.
Polio24_006 | Ongoing Investigation of Polio Recurrance | Province: Verdantis | Health Zone: Azure Reach | Health Area: Lumoria | 2024-07-31 | 2024 | Q3 | https://www.LINK TO SHARED FOLDER.org |  |  |  | Implement training programs on the maintenance and monitoring of communal sewage facilities.​ | Enhance the capability of local personnel to effectively manage and maintain communal sewage facilities through targeted training programs. | Program Intervention | Global | Training attendance lists and evaluation results. | Sanitary Training Institute | Emily Watson, emily@sanitarytraining.com, +564-738-2910 | National/Local Non-Governmental Organization (NGO) | Education | 2024-08-10 | 2024-09-10 | In-Progress | N/A | https://www.LINK TO VERIFICATION DOC.org | Number of personnel trained, improvement in maintenance quality. | Enhanced skills among maintenance staff, prolonged facility lifespan. | Assessor's Information: Emily Brown, Training Coordinator Evidence/Documentation: Participant lists and feedback forms. Next Steps: Conduct advanced training sessions and reassess skill levels.
Polio24_007 | Ongoing Investigation of Polio Recurrance | Province: Verdantis | Health Zone: Azure Reach | Health Area: Lumoria | 2024-07-22 | 2024 | Q3 | https://www.LINK TO SHARED FOLDER.org |  |  | Lack of public trust and awareness about proper waste disposal | Improve and maintain community latrines with consideration for privacy, cleanliness (e.g., regular cleaning schedules, handwashing stations), and safety to increase communal trust and usage. | Upgrade community latrines to meet higher standards of privacy, cleanliness, and safety, thereby fostering trust and encouraging widespread use. | Direct Change to Strategy | Women | Inspection reports and usage statistics. | Ministry of Health | Roberto Alvarez, roberto@usd.gov, +213-864-1309 | Ministry of Health | Water, Sanitation, & Hygiene (WASH) | 2024-08-01 | 2024-09-01 | Abandoned | Funding withdrawal. | https://www.LINK TO VERIFICATION DOC.org | Usage rates, cleanliness standards. | N/A - action abandoned. Anticipated improved hygiene practices and reduced health risks. | Assessor's Information: Jane Blue, Public Health Officer Evidence/Documentation: Initial inspection reports. Next Steps: Seek alternative funding sources to restart the project.
Polio24_008 | Ongoing Investigation of Polio Recurrance | Province: Verdantis | Health Zone: Azure Reach | Health Area: Lumoria | 2024-07-18 | 2024 | Q3 | https://www.LINK TO SHARED FOLDER.org |  |  |  | Conduct health and sanitation education campaigns | Educate the community on health and sanitation practices to improve public health outcomes and promote sustainable sanitation behaviors. | Program Intervention | Global | Campaign reach reports and audience engagement metrics. | Local Health Authority | Maria Lopez, maria@healthaware.org, +890-567-1234 | Local Health Authorities | Risk Communication and Community Engagement (RCCE) | 2024-08-18 | 2024-09-18 | Completed | N/A | https://www.LINK TO VERIFICATION DOC.org | Number of participants, change in public health knowledge. | Increased awareness of health and sanitation, behavior change. | Assessor's Information: Sarah Red, Community Educator Evidence/Documentation: Campaign analytics and survey results. Next Steps: Expand the campaign to additional communities based on success metrics.

## Observations from Analysis
Health Province, Region, State, etc. | Health District, Region, Zone, Jurisdiction, Division, etc. | Health Precinct, Sector, Territory, Area, Unit, Locale, etc. | Analysis Code | Year of Analysis (yyyy) | Title of the Analysis | Key Risks/Observations | Contributing Factors | Underlying Causes | Was the Underlying Cause Used to Co-Develop an Action | Reason for Not Using the Underlying Cause to Co-Develop an Action | If Actions were Co-Developed, List the Code Assocated with the Action(s) | Implementation Status
List the geographic administative divison in your country where the public health emergency is occuring. This could be a province, state, region, or similar area. | Provide the specific health district, region, zone, jurisdiction, or division within the geographic administrative division (such as a province, state, or region) previously listed, where the public health emergency is occurring. This should be a more localized area within the broader administrative division you identified. | Specify the precise health precinct, sector, territory, area, unit, or locale within the broader health district, region, zone, jurisdiction, or division you previously identified. This should pinpoint the most localized area where the public health emergency is taking place, nested within the larger geographic administrative division (such as a province, state, or region) you listed earlier. | Create a unique code designed specifically for each analsis. Every analysis should have its own distinct code. For example, the first analysis completed during a polio outbreak in 2024 might be assigned a code such as 'Analysis_Polio24_HealthArea001'. | List the year that the analysis was conducted. | Create a unique title for each analysis. Example: 'Integrated Analysis of the Determinants of Recurring Polio in Health Area 2024'. | List the key risks and observations linked ot the co-developed aciton. For instance, in the case of a recurring polio outbreak, a noteable risk could be that infants are not receiving vaccinations. | List the contributing factors associated with the co-developed action. For instance, a contributing factor for infants not receiving vaccinations could be the prevalence of at-home deliveries, which often result in reduced access to post-natal care. | List the underlying causes associated with the co-developed action. For example, the high prevalence of at-home deliveries, leading to infants missing post-natal care such as vaccinations, can be attributed to the high cost of helathcare services and insufficient transportation to clinics. | Indicate whether the underlying cause was used to co-develop an action by selecting 'Yes,' 'No,' or 'Pending'. | Explain why the underlying cause was not used to co-develop an action. If you previously selected 'pending' for this item, please specify the reasons for the delay in using the underlying cause to formulate an action. | Create a unique code designed specifically for each co-developed action. Every action should have its own distinct code. For example, an action co-developed during a polio outbreak in 2024 might be assigned a code such as 'Polio24_001'. Ensure that this code corresponds to the code listed in column A on the first tab of this Excel spreadsheet. | Select the implementation status category for the action from the following options: completed, in-progress, delayed/not yet started, or abandoned.
Province: Verdantis | Health Zone: Azure Reach | Health Area: Lumoria | Analysis_Polio2024_Lumaria001 | 2024 | Integrated Analysis of the Determinant of Recurring Polio in Lumaria 2024 | Poor Sanitation in Lumoria. Poor sanitation is linked to malnutrition, which can compromise the immune system and diminish vaccine effectiveness. This weakened immune response increases vulnerability to diseases such as polio. | Lack of access to clean water | Inadequate infrastructure in Lumoria due to limited funding and/or prioritization of water treatment projects | Yes | N/A | Polio24_001 | In-Progress
[11 empty] | Polio24_002 | Completed
[8 empty] | Travel to areas with access to clean water is unsafe | Yes | N/A | Polio24_003 | Delayed/Not Yet Started
[11 empty] | Polio24_004 | In-Progress
[7 empty] | Poor waste disposal | Inadequate maintenance of sewage systems leads to community concerns about disease risks associated with using communal latrines | Yes | N/A | Polio24_005 | Completed
[11 empty] | Polio24_006 | In-Progress
[8 empty] | Lack of public trust and awareness about proper waste disposal | Yes | N/A | Polio24_007 | Abandoned
[11 empty] | Polio24_008 | Completed

## Drop Down Lists
Actor/ Partner Category | Sector [of Partner] Accountable for the Action | Action Category | Population Affected by the Action | Implementation Status | Was the Underlying Cause Used to Co-Develop an Action
Civil Society Group | Agriculture | Advocacy for Financing | Children | Completed | Yes
Community | Camp Coordination & Camp Management (CCCM) | Advocacy for New Strategy Development | Global | In-Progress | No
International Non-Governmental Organization (INGO) | Disease Specific Sector (e.g., cholera, polio, mpox) | Direct Change to Strategy | Men | Delayed/Not Yet Started | Pending
Local Health Authorities | Early Recovery | New Program Development & Implementation | Women | Abandoned
Ministry of Agriculture | Education | Program Intervention
Ministry of Commerce | Emergency
Ministry of Education | Environment
Ministry of Environment | Food Security & Nutrition
Ministry of Health | Health
Ministry of Housing | Labour
Ministry of Labour | Logistics
Ministry of Social Welfare | Other (Not Listed)
Ministry of Transportation | Protection including Gender-based Violence (GBV)
National/Local Non-Governmental Organization (NGO) | Research
National Government | Risk Communication and Community Engagement (RCCE)
Other Ministry (Not Listed) | Shelter & Non-Food Items
Provincial/Local Government | Water, Sanitation, & Hygiene (WASH)
UN Agency